## Agile Product Backlog
SPRINT BACKLOG | [9 empty] | 1 Story = 2 Hours
SPRINT # | TASK NAME | User Story | Complexity | PRIORITY | Return on Investment | ASSIGNED TO | STORY POINTS | START | FINISH | STATUS | Date comlpeted | Velocity 1 | Velocity 2
Sprint 1 | [11 empty] | 75
| Create the website, include all input fields | The user can view all data from the data set | 3 | 10 | 3.3333 | Tony, Joel, Michael | 8 | 27/01/20 | 28/01/20 | Complete | 27/01/20 | This section is for the drop-down list
| Display data set front end template (updated 29th to break up tasks as the database was not ready to take data from) |  | 2 | 10 | 5 | Tony, Joel | 4 | 27/01/20 | 28/01/20 | Complete | 30/01/20 | Yes | High | Complete
| Display data set |  | 2 | 10 | 5 | Tony, Joel, Dimitar | 4 | 28/01/20 | 29/01/20 | In Progress | ..
| Create a database (added 28th when we decided to use an sql database to search through the dataset as it is so large) |  | 1 | 10 | 10 | Jodie | 1 | 28/1/20 | 28/1/20 | Complete | 28/01/20
| Populate database |  | 3 | 10 | 3.3333 | Jodie, Michael | 3 | 28/1/20 | 28/1/20 | Complete | 29/01/20
| Include a map on the website | Results from a search can be indicated on the map | 3 | 9 | 3 | Michael | 4 | 27/01/20 | 28/01/20 | Complete | 29/01/20
| Set up display icon pins (displaying relevant data at the relevant location) - added 30/01/2020 to add more detail and break up the task |  | 3 | 8 | 2.6667 | Michael | 4 | 29/01/20 | 30/01/20 | Complete | 30/01/20
| Create search by code function | The user can search by code | 2 | 9 | 4.5 | Ben | 4 | 27/01/20 | 28/01/20 | Complete | 28/01/20
| Create search by procedure function | The user can search by procedure | 2 | 9 | 4.5 | Ben | 2 | 28/01/20 | 29/01/20 | Complete | 28/01/20
| Create search by location function | The user can search by location | 2 | 8 | 4 | Ben | 2 | 28/01/20 | 29/01/20 | Complete | 28/01/20
| Create an order by distance function | The user can order results based on distance | 3 | 7 | 2.3333 | Ben | 2 | 28/01/20 | 29/01/20 | Complete | 30/01/20 | No | Medium | In Progress
| Create an order by price function | The user can order results based on price | 3 | 7 | 2.3333 | Ben | 2 | 28/01/20 | 29/01/20 | Complete | 28/01/20
| Calculate distance between two locations | The user can restrict their search to a distance range, so they can find the nearest options available | 2 | 6 | 3 | Jodie | 3 | 29/01/20 | 30/01/20 | Complete | 28/01/20
| Create function to restrict search to a distance range |  | 1 | 6 | 6 | Jodie | 2 | 29/01/21 | 30/01/21 | Complete | 28/01/20
| Create function to restrict search to a price range | The user can restrict their search to a price range, so that the user can find the cheapest options available | 3 | 6 | 2 | Jodie | 2 | 29/01/20 | 30/01/20 | Complete | 27/01/20
| Link java functions to SQL database - added 30/01/2020 to add more detail and break up the task |  | 4 | 10 | 2.5 | Jodie | 5 | 30/01/20 | 31/01/20 | Complete | 29/01/20
| Call java functions from HTML - added 30/01/2020 to add more detail and break up the task |  | 4 | 10 | 2.5 | Tony, Joel | 5 | 30/01/20 | 31/01/20 | Complete | 30/01/20
| Merge all tasks together |  | 3 | 10 | 3.3333 | All |  | 30/01/20 | 31/01/20 | In Progress | ..
| Merge functional map into HTML - added 30/01/2020 to add more detail and break up the task |  | 8 | 9 | 1.125 | Tony, Michael | 8 | 30/01/21 | 31/01/21 | In Progress | ..
| Merge HTML front end with back end search function: search by code, distance, procedure |  | 3 | 9 | 3 | All | 5 | 30/01/22 | 31/01/22 | In Progress | ..
| Merge HTML front end with back end search function: restrict search by distance, price |  | 4 | 9 | 2.25 | All | 5 | 30/01/23 | 31/01/23 | In Progress | ..
| Merge HTML front end with back end search function: order by price, distance |  | 4 | 9 | 2.25 | All | 5 | 30/01/24 | 31/01/24 | In Progress | ..
Sprint 2 | [6 empty] | 80 | [5 empty] | Low | Not Started
| Display a combination of search results in one list | The user can view the results as a ranked list, based on a combination of information | 5 | 3 | 0.6 | Dimitar | 2 | 2020-04-02 | 2020-05-02 | In Progress | ..
| Merge all tasks together |  | 3 | 10 | 3.3333 | All |  | 2020-04-02 | 2020-05-02 | In Progress | ..
| Merge functional map into HTML - added 30/01/2020 to add more detail and break up the task |  | 8 | 9 | 1.125 | Tony, Michael | 8 | 2020-04-02 | 2020-05-02 | In Progress | ..
| Merge HTML front end with back end search function: search by code, distance, procedure |  | 3 | 9 | 3 | All | 5 | 2020-03-02 | 2020-05-02 | In Progress | ..
| Merge HTML front end with back end search function: restrict search by distance, price |  | 4 | 9 | 2.25 | All | 5 | 2020-04-02 | 2020-05-02 | In Progress | ..
| Merge HTML front end with back end search function: order by price, distance |  | 4 | 9 | 2.25 | All | 5 | 2020-04-02 | 2020-05-02 | In Progress | ..
| Intergrate search results into map |  |  |  |  | Michael |  | 2020-03-01 | 2020-04-01 | In Progress
| Include a map with placeholder for all search results | Results from a search can be indicated on the map using a placeholder, also displaying price information | 3 | 6 | 2 | Tony, Michael | 2 | 2020-03-02 | 2020-04-02 | Not Started
| Display name of establishment, location and price when mouse over placeholder |  | 2 | 6 | 3 | Tony, Michael | 4 | 2020-04-02 | 2020-05-02 | Not Started
| Display additional details for search results | The user can view additional details for their search results | 3 | 7 | 2.3333 | Jodie | 2 | 2020-03-02 | 2020-04-02 | Not Started
| Create an option to use the device's location as input for searches using location | The user's location can be derived from device location | 3 | 5 | 1.6667 | Tony | 1 | 2020-05-02 | 2020-06-02 | Not Started
| Add screen reader functionality | The product is accessible by all user groups | 1 | 4 | 4 | Joel | 1 | 2020-04-02 | 2020-05-02 | Not Started
| Add text resize options |  | 1 | 4 | 4 | Joel | 1 | 2020-04-02 | 2020-05-02 | Not Started
| Add text/image colour options |  | 1 | 4 | 4 | Joel | 1 | 2020-04-02 | 2020-05-02 | Not Started
| Create a function to add data to the existing data set | The Centers for Medicare & Medicaid can to load new data to the existing dataset | 2 | 3 | 1.5 | Ben | 1 | 2020-05-02 | 2020-06-02 | Not Started
| Create a function to delete the existing data set | The Centers for Medicare & Medicaid can delete existing data from the existing dataset | 2 | 3 | 1.5 | Ben | 2 | 2020-05-02 | 2020-06-02 | Not Started
| Create a function to edit the existing data set | The Centers for Medicare & Medicaid can edit existing data in the data set | 2 | 3 | 1.5 | Ben | 2 | 2020-05-02 | 2020-06-02 | Not Started
| Record user input data |  | 1 | 2 | 2 | Jodie | 2 | 2020-04-02 | 2020-07-02 | Not Started
| Analyse data and look for patterns/trends | software can provide machine learning based on user selection | 4 | 2 | 0.5 | Jodie | 4 | 2020-04-02 | 2020-07-02 | Not Started
| Output relevent data based on analysis |  | 2 | 2 | 1 | Jodie | 3 | 2020-04-02 | 2020-07-02 | Not Started
| Merge all tasks together |  | 2 | 10 | 5 | Jodie, Tony, Joel, Ben | 4 | 2020-06-02 | 2020-07-02 | Not Started

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.