## Sheet1
|  |  | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31
User Stories/Tasks | Initial Estimate (hours) | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | 1 Story Point = 2 hours
Create the website, include all input fields | 8 |  |  |  | 8
Import data set | 4 |  |  |  | 4
Display data set | 4
Create database |  |  | -1 |  | 1
Populate database |  |  | -3 |  | 3
Include a map on the website | 4 |  |  | 4
Set up display icon pins (displaying relevant data at the relevant location) | 4 |  |  | -2 | 6
Link the pinned locations to the search results | 5
The user can search by code | 4 |  |  | 4
The user can search by procedure | 2 |  |  | 2
The user can search by location | 2 |  |  | 2
The user can order results based on distance | 2 |  | -2 |  |  | 4
The user can order results based on price | 2 |  |  | 2
The user can restrict their search to a distance range | 5 |  |  | 5
The user can restrict their search to a price range | 4 |  | 4
The user can view the results as a ranked list based on combination of information | 5
Merge all tasks together | 5 |  |  |  | -10
| Remaining Effort | 60 | 62 | 45 | 33 | 29 | 29
| Ideal Trend | 60 | 48 | 36 | 24 | 12 | 0
| Legend: | Missing at Start
Added to Sprint
Projected Value