## Sheet1
Sprint Burndown |  |  | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31
User Stories/Tasks | Initial Estimate | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | 1 Story Point = 2 hours
Create the website, include all input fields | 8 |  |  |  | 8
Display data set front end template | 4 |  |  |  | 4
Display data set | 4
Create database |  |  |  | -1 | 1
Populate database |  |  |  | -3 | 3
Include a map on the website | 4 |  |  | 4
Set up display icon pins (displaying relevant data at the relevant location) | 4 |  |  | -2 | 6
Link the pinned locations to the search results | 5
The user can search by code | 4 |  |  | 4
The user can search by procedure | 2 |  |  | 2
The user can search by location | 2 |  |  | 2
The user can order results based on distance | 2 |  | -2 |  |  | 4
The user can order results based on price | 2 |  |  | 2
The user can restrict their search to a distance range | 5 |  |  | 5
The user can restrict their search to a price range | 4 |  | 4
The user can view the results as a ranked list based on combination of information | 5
Link Java functions to SQL database | [5 empty] | -5
Call Java functions from HTML | [5 empty] | -6
Map template uses search results from the user input
Merge HTML front end with back end search function: search by code, distance, procedure
Merge HTML front end with back end search function: restrict search by distance, price
Merge HTML front end with back end sarch function: Order by price, distance | [7 empty] | Legend: | Missing at Start | TODO: Velocity
Finish merging all tasks together | 5 |  |  |  | -10 |  |  |  | Added to Sprint later
| Remaining Effort | 60 | 58 | 45 | 33 | 40 | 40 |  | Projected Value
| Ideal Trend | 60 | 48 | 36 | 24 | 12 | 0