## Sheet1
PRODUCT BACKLOG
| User Story | Complexity | ESTIMATE | CONVERSATION | STATUS
| The user can view all data from the data set | 10 | 9 |  | In progress
| The user can search by location | 8 | 2 |  | Complete
| The user can order results based on distance | 7 | 2 |  | Complete
| The user can order results based on price | 7 | 2 |  | Complete
| The Centers for Medicare & Medicaid can to load new data to the existing dataset | 3(optional) | 7 |  | Not started
| The Centers for Medicare & Medicaid can edit existing data in the data set | 3(optional) | 7 |  | Not started
| The Centers for Medicare & Medicaid can delete existing data from the existing dataset | 3(optional) | 7 |  | Not started
| The user can restrict their search to a price range, so that the user can find the cheapest options available | 6 | 5 |  | Complete
| The user can restrict their search to a distance range, so they can find the nearest options available | 6 | 5 |  | Complete
| The user's location can be derived from user input | 7 | 3 |  | Complete
| The user's location can be derived from device location | 5 | 3 |  | Not started
| The user can view the results as a ranked list, based on a combination of information | 3(optional) | 7 |  | In progress
| The product is accessible by all user groups | 4 (optional) | 8 |  | Not started
| software can provide machine learning based on user selection | 2 (optional) | 10 |  | Not started
| Results from a search can be indicated on the map using a placeholder, also displaying price information | 6 | 9 |  | In progress
| The user can view additional details for their search results | 7 | 7 |  | Not started
| The user can search by code | 9 | 2 |  | completed
| The user can search by procedure | 9 | 2 |  | completed